Green PM  v5

Decision Centre

Governance Backbone — Decision Engine — Technical Reference

Version 5.0  |  August 2026

1.  What Is a Decision?

The Decision Centre is Green PM's governance backbone. Every formal determination that affects the project passes through the Decision Engine — a 10-state lifecycle that captures, routes, approves, implements, and learns from every consequential project decision.

A Decision in Green PM is any formal determination that:

- Changes the project baseline — scope, schedule, cost, or quality parameters

- Resolves a risk or issue — selects a mitigation path and commits to it

- Approves a change order — formally authorises a scope or cost change and its downstream effects

- Selects between competing options — when two or more valid paths exist and a commitment is required

- Closes a pending action — formally declares that an identified action has been taken and the matter is resolved

Decisions are NOT:

- Informal verbal agreements — these are not tracked in Green PM; only formal decisions with a record and an approver

- Routine approvals — standard sign-offs that are part of a defined workflow (e.g., timesheet approval, routine inspection sign-off) are handled by the Approval Chain Builder, not the Decision Engine

- System-generated recommendations — the Recommendation Engine produces recommendations, not decisions; a recommendation becomes a decision only when a human approves it and it is captured as a Decision record

- AI outputs — Green PM's AI outputs (narrative summaries, impact analyses, forecasts) are advisory; the human who acts on them creates the Decision record

Why this matters:

EPC project failures are rarely caused by lack of information. They are caused by poor governance — decisions made informally, without evidence, without accountability, and without institutional memory. The Decision Centre exists to make governance systematic: every consequential decision is captured, evidence-backed, properly approved, implemented, monitored, and remembered for the next project.

2.  Decision States — 10-State Lifecycle

Every Decision in Green PM follows a 10-state lifecycle. State transitions are logged immutably. Each transition triggers PIG edge updates and notifications per the Notification Rule Builder configuration.

| State | Description | Who Can Trigger | PIG Edges Written | Notifications Sent |
| --- | --- | --- | --- | --- |
| DRAFT | Decision record created but not yet submitted for review. Submitter can edit all fields. Not visible to approvers. | Created by any authorised role via decision create event or Recommendation Engine approval | CREATED_BY edge: Decision → Person; TRIGGERS edge if created from risk/change entity | None — draft decisions do not generate notifications |
| PENDING_REVIEW | Decision submitted for review. Enters the approval queue of the first approver in the chain. Fields are locked. | Submitter action: 'Submit for Review' | REVIEWS edge: Decision → first approver role; IMPACTS edges to all affected entities | Notification to first approver role; PCC Panel 8 count updates |
| UNDER_REVIEW | First approver has opened the decision and is actively reviewing. Timer for dual-approval starts if configured. | Approver action: 'Start Review' | REVIEWED_BY edge: Decision → current approver Person node (runtime resolution) | Notification to submitter confirming review started |
| APPROVED | All required approvers have approved. Decision is enacted. | Final approver action: 'Approve'; dual-approval: second approver action after first confirmed | APPROVED_BY edges: Decision → each approver; CLOSES edge if decision closes a risk/change | Notification to all stakeholders per rule; PCC Panel 8 resolved; Coordination Engine creates implementation items |
| REJECTED | One or more required approvers have rejected the decision. Returns to submitter. | Any required approver action: 'Reject' with reason | REJECTED_BY edge: Decision → rejector; rejection_reason stored on Decision node | Notification to submitter with rejection reason; escalation if configured |
| DEFERRED | Decision has been acknowledged but a determination has been deliberately postponed. | Any approver or Project Director action: 'Defer' with reason and defer-until date | DEFERRED_BY edge with defer_until timestamp | Notification to submitter; re-enters PENDING_REVIEW queue at defer_until date automatically |
| IMPLEMENTATION | Decision approved; implementation is actively underway. Coordination items are open. | Automatic: triggered when Coordination Engine creates implementation coordination items from APPROVED transition | MONITORS edges: Decision → all open coordination items generated from this decision | Notification to coordination item assignees; Panel 8 shows implementation progress |
| MONITORING | Implementation complete; monitoring period active to verify the decision's actual outcome matches the projected outcome. | Coordination Engine: all implementation coordination items closed | MONITORS edge updated: implementation closed; new MONITORING edges added | Notification to decision owner and Project Director that monitoring period has started |
| CLOSED | Decision fully resolved — implementation verified, outcome confirmed, memory record created. | Decision owner or Project Director: 'Close' with outcome_verified_at and outcome summary | CLOSED_BY edge; CONTRIBUTES_TO edge: Decision → memory_record (pending PM approval) | Notification to all stakeholders; Organizational Memory Engine update queued for PM approval |
| ARCHIVED | Decision record preserved for audit and institutional memory; no further actions possible. | Automatic: 90 days after CLOSED, or manual by Studio Admin | ARCHIVED_AT timestamp; all existing edges preserved | No notification — archive is a background housekeeping action |

State transition rules:

- Forward transitions are generally one-way — a CLOSED decision cannot return to IMPLEMENTATION

- REJECTED decisions can be re-submitted as new DRAFT records with a new evidence set — re-submission creates a link between the old and new record (SUPERSEDES edge)

- DEFERRED decisions automatically re-enter the PENDING_REVIEW queue at the configured defer-until date via Cloud Scheduler

- All state transitions are synchronised to Firestore — PCC Panel 8 updates in real time on every transition

3.  Decision Record — Fields

Every Decision is a structured record in the decisions table. The record captures the decision itself, its governance trail, its evidence basis, and its outcome. All fields are indexed. The decisions table is tenant-scoped.

| Field | Type | Required | Description |
| --- | --- | --- | --- |
| id | UUID | Yes | Primary key — system-generated UUID v4; immutable after creation |
| project_id | UUID | Yes | Foreign key to projects table — all decisions are project-scoped; cross-project decision lookup is via Organizational Memory Engine only |
| tenant_id | UUID | Yes | Foreign key to tenants table — tenant isolation enforced at row level via Row-Level Security in PostgreSQL |
| title | Text (max 200) | Yes | Concise human-readable decision title — shown in PCC Panel 8, approval queues, and all notifications (e.g., 'Approve Change Order CO-0042: Scope Extension South Substation') |
| description | Text (long) | Yes | Full description of the decision, the context, and the problem being resolved — this is the narrative the approver reads |
| decision_type | Enum | Yes | Classifies the decision: scope_change / schedule_change / cost_change / risk_mitigation / change_order / vendor_action / regulatory / design_change / resource_change / other |
| trigger_entity_type | Enum | No | The entity type that triggered this decision being raised: Change / Risk / Recommendation / Issue / Gate / Milestone / null (manually raised) |
| trigger_entity_id | UUID | No | The specific entity that triggered this decision — used to write the TRIGGERS PIG edge from the source entity to this Decision node |
| status | Enum | Yes | Current lifecycle state — one of the 10 states in Section 2; updated on every state transition |
| options_considered | JSONB | No | Array of options evaluated before selecting the recommended option — each option has: option_id, description, pros, cons, estimated_cost_impact, estimated_schedule_impact |
| selected_option | Text | No | The option chosen — references option_id from options_considered; populated at APPROVED transition |
| rationale | Text (long) | No | Narrative explanation of why the selected option was chosen over alternatives — recorded at APPROVED transition; required if options_considered is populated |
| evidence_refs | UUID array | No | Array of Evidence node IDs from the PIG that support this decision — each ref links to an evidence record with its capture type, source, timestamp, and reliability score; decisions with empty evidence_refs trigger a warning |
| approver_chain | JSONB | Yes | Configured approval chain for this decision — copied from Approval Chain Builder at decision creation; records: role, order, parallel_flag, timeout_hours, escalation_role |
| current_approver_role | Text | No | The role currently holding this decision for action — null if in DRAFT, APPROVED, REJECTED, DEFERRED, IMPLEMENTATION, MONITORING, CLOSED, or ARCHIVED |
| approved_by | UUID array | No | Array of Person node IDs of users who approved this decision — populated progressively as each approver acts; must satisfy approval_threshold before status transitions to APPROVED |
| approved_at | Timestamp with TZ | No | Timestamp of the final approval action that transitioned status to APPROVED — UTC |
| rejection_reason | Text | No | Free-text rejection reason — required when status transitions to REJECTED; displayed to submitter in notification |
| implementation_notes | Text | No | Notes recorded during IMPLEMENTATION state — progress updates, issues encountered, deviations from plan; appended, not overwritten |
| outcome_verified_at | Timestamp with TZ | No | Timestamp when the decision outcome was verified and confirmed — required to transition from MONITORING to CLOSED |
| memory_approved | Boolean | No | Whether the decision outcome record has been approved by the Project Manager for ingestion into the Organizational Memory Engine — defaults to false; set to true by PM action; Organizational Memory Engine only processes records where this is true |
| created_by | UUID | Yes | Person node ID of the user who created this decision record — immutable after creation |
| created_at | Timestamp with TZ | Yes | Record creation timestamp — UTC; immutable after creation |
| updated_at | Timestamp with TZ | Yes | Last update timestamp — UTC; updated on every field change and state transition |

4.  Institutional Learning — The Memory Link

The Decision Engine is one of only two engines that both reads from and writes to the Organizational Memory Engine (the other is the Risk Engine). This bidirectional link is what transforms Green PM from a project management tool into an institutional learning system.

4.1  How the Memory Link Works at Decision Creation

When a decision is created, the Decision Engine immediately queries the Organizational Memory Engine:

- Query: 'Find completed decisions of type X from this tenant and from similar project types'

- Parameters used in the similarity match: decision_type, trigger_entity_type, estimated cost impact range, estimated schedule impact range

- Return: up to 5 similar past decisions — including the options that were considered, the option selected, the actual outcome, and the confidence score of the match

The institutional memory panel displays alongside the decision record:

"In 27 similar change order decisions on comparable EPC projects, Option B (fast-track approval with 3-week schedule compression) reduced schedule impact by 18% on average compared to Option A (standard approval with full re-baseline). Confidence: 0.74."

This information is displayed as advisory context — it is not a recommendation (the Recommendation Engine produces recommendations). The human decision-maker reviews the memory context and makes the final determination. Green PM presents the pattern; the human exercises judgment.

4.2  How the Memory Link Works at Decision Closure

When a decision is closed with a confirmed outcome, the Decision Engine prepares a memory record for ingestion into the Organizational Memory Engine. The record includes:

- Decision type, trigger context, options considered

- Selected option and the rationale given at approval

- Actual outcome: actual schedule impact vs projected, actual cost impact vs projected

- Outcome delta: was the decision's projected benefit realised? By how much?

- Project context: project type, region, scale, phase

The memory record is flagged as memory_approved = false until the Project Manager reviews and approves it. The Organizational Memory Engine only processes records where memory_approved = true — this human gate prevents degraded decisions from polluting the institutional memory.

Over time, the Organizational Memory Engine accumulates a library of decision outcomes that power: Decision Engine institutional learning, Simulation Engine historical calibration, and Risk Engine pattern detection — across all projects in the tenant.

5.  Dual-Approval Pattern

For high-value decisions, Green PM enforces a dual-approval pattern — two separate approvers must independently confirm approval before the decision transitions to APPROVED. This provides a governance safeguard against single-point-of-failure in approvals for the most consequential project determinations.

5.1  Trigger Thresholds (Configurable)

Dual approval is triggered when either condition is met:

- Schedule impact > 14 calendar days — default; configurable in Studio (Approval Chain Builder, 'Dual Approval Required' toggle + threshold)

- Cost impact > INR 50 lakh (INR 5,000,000) — default; configurable per tenant in Studio

- Decision type = 'schedule_change' or 'scope_change' — these types always trigger dual approval regardless of magnitude (configurable override)

5.2  Dual-Approval Sequence

- First approver acts — approves with rationale; Decision Engine records first approval in approved_by array and confirmation timestamp

- Second approver notified — only after first approval is confirmed; second approver is a different role from the first

- Second approver acts — independently reviews and approves (or rejects; rejection by either approver blocks the decision)

- 409 CONFLICT guard — if the second approval is attempted before the first is confirmed in the database, the API returns 409 CONFLICT to prevent race conditions in concurrent approval workflows

- Both approvals confirmed — Decision Engine transitions status to APPROVED; writes both APPROVED_BY PIG edges

5.3  Timeout and Escalation

- Timeout: 48 hours per approver — if no action is taken within 48 hours, the decision is escalated to the configured escalation role

- Escalation notification: immediate push notification + in-app alert to the escalation role

- Maximum escalation: one level above configured approver — escalation does not continue indefinitely

- Timer reset: the 48-hour timeout resets when the escalation role receives the decision; total maximum elapsed time is 96 hours before the decision is flagged as critically overdue in PCC Panel 8

6.  Evidence Requirements

Every decision must cite evidence to be credible. The Decision Engine enforces an evidence requirement — not as a hard block, but as a guardrail that makes the absence of evidence visible to every approver.

6.1  Evidence Citation

- evidence_refs[] is an array of Evidence node IDs from the PIG — these are real evidence records with capture type, source, timestamp, and reliability score

- A decision with evidence_refs.length = 0 is permitted — but the UI displays a prominent warning: 'No evidence cited for this decision'

- The warning is visible to all approvers in the approval interface — they see exactly how many evidence items are cited and can click through to review each one

- Approvers can reject a decision specifically citing insufficient evidence — the rejection_reason field captures this

6.2  Evidence Quality Display

For each cited evidence item, the Decision Engine displays:

- Evidence type (photo, video, inspection record, test certificate, etc.)

- Source reliability score (from Evidence Engine source reliability mapping)

- Capture timestamp and operator

- Computed Evidence Score component this item contributes to the activity it is linked to

This evidence quality display serves two purposes: it tells the approver how strong the evidential basis is, and it creates a permanent record that the approver was shown the evidence before making their determination. This record is part of the immutable audit trail.

6.3  Evidence Sufficiency Guidance (Organizational Memory)

For each decision type, the Organizational Memory Engine can provide guidance on evidence that has been cited in similar past decisions — what types of evidence were most commonly cited, and whether evidence volume correlated with better decision outcomes. This is surfaced as advisory context in the decision workspace, not as a rule.

7.  Integration with Other Engines

The Decision Engine sits at the governance centre of Green PM — it receives inputs from many engines and produces outputs consumed by many others. Every significant project event ultimately creates or updates a Decision.

| Engine | Interaction with Decision Engine |
| --- | --- |
| Change Intelligence Engine | Every change order above the configured value threshold automatically generates a Decision record in DRAFT state with decision_type = 'change_order'. The Change entity is linked to the Decision via the TRIGGERS PIG edge. The Decision's impact summary is pre-populated from the Change Intelligence Engine's impact analysis. Approval of the Decision transitions the Change to approved state. |
| Risk Engine | High-severity risks (configurable threshold — default: probability × impact score > 0.6) automatically generate a Decision record of type 'risk_mitigation'. The Risk entity is linked to the Decision via TRIGGERS edge. If no mitigation decision is in progress for a high-severity risk, Risk Engine escalates and raises an alert. Closed mitigation decisions update the Risk's mitigation_status field. |
| Recommendation Engine | When a user approves a recommendation in the Recommendation Engine workspace, a Decision record is created in DRAFT state with the recommendation's evidence_refs, impact projections, and recommended option pre-populated. The Recommendation Engine does not create Decisions autonomously — it requires a human approval action to initiate the Decision lifecycle. |
| Organizational Memory Engine | Bidirectional: (1) Decision Engine queries Organizational Memory at Decision creation to surface similar past decisions as advisory context for approvers. (2) When a Decision is CLOSED with a verified outcome and memory_approved = true, Decision Engine writes a memory_record to the Organizational Memory Engine capturing the decision type, options, selected option, rationale, and actual vs projected outcome. |
| Coordination Engine | When a Decision transitions to APPROVED, the Coordination Engine automatically creates coordination items for each implementation action identified in the approver's sign-off notes and in the selected option's implementation plan. These coordination items are linked to the Decision via MONITORS edges. Panel 8 shows implementation progress against these items. |
| Impact Analysis Engine | Before the APPROVED transition is presented to an approver, the Impact Analysis Engine runs a PIG traversal to compute the full downstream impact of the selected option: schedule impacts (activities delayed, float consumed), cost impacts (budget reallocation, additional spend), quality impacts (rework required), and supply chain impacts (dispatches affected). The approver sees the full impact chain before committing. |
| Reporting Engine | The Reporting Engine includes a Decisions section in weekly and monthly reports — showing decisions resolved, decisions pending, approval throughput (decisions closed vs raised per period), and average approval cycle time. Decision Centre analytics are also available as a standalone report type ('Governance Dashboard'). |
| Forecasting Engine | Approved decisions with schedule impact are fed to the Forecasting Engine to update the schedule model: baseline revision if the decision changes the approved baseline, or forecast revision if it is within the current contingency range. Cost impact from approved decisions updates the cost forecast model. |
| AI Orchestration Engine | The AI Copilot ('Ask Green PM') can query the Decision Centre: 'What decisions are pending my approval?', 'What is the evidence basis for Decision DC-0087?', 'What did we decide the last time we had a similar scope change?'. The AI Orchestration Engine routes these queries to the Decision Engine and Organizational Memory Engine. The AI never creates, updates, or approves Decisions — all write actions require a human. |
| Synchronization & Consistency Engine | When a Decision is APPROVED that changes a project parameter (e.g., approves a revised drawing), the Synchronization & Consistency Engine checks that all related entities (schedule activities, vendor submittals, procurement packages) are updated to reflect the new parameter. If inconsistencies are found, it generates alerts and creates coordination items via the Coordination Engine. |

8.  Decision Audit Trail

Every state transition of every Decision is logged in an immutable audit trail. The audit trail is the permanent record that the decision was made, by whom, when, on what evidence, and through what governance process. It is the accountability record of the project.

8.1  Audit Log Structure

Every audit log entry (decision_audit_log table) contains:

| Field | Type | Description |
| --- | --- | --- |
| id | UUID | Primary key — immutable |
| decision_id | UUID | Reference to the Decision record — indexed for fast audit trail retrieval |
| event_timestamp | Timestamp with TZ | Exact UTC timestamp of the state transition or field change — immutable |
| actor_id | UUID | Person node ID of the user who triggered this event — resolved from authentication context, not user-supplied |
| actor_role | Text | The role the actor was acting in at the time of the event — snapshot, not current role (roles can change) |
| from_state | Enum | Previous Decision state before this event |
| to_state | Enum | New Decision state after this event |
| fields_changed | JSONB | For non-state-transition events: map of field name to { previous_value, new_value } — null for state transitions |
| notes | Text | Approver notes, rejection reasons, or deferral explanations recorded at the time of the action — verbatim, immutable |
| evidence_snapshot | UUID array | Snapshot of evidence_refs at the time of this event — preserves the evidence state at each approval milestone |
| ip_address | Text | IP address of the actor at the time of the event — for forensic audit purposes; never displayed in UI |
| session_id | UUID | Session ID of the actor's authenticated session — for forensic audit purposes |

8.2  Audit Trail Access

- Accessible to: all roles with read access to the Decision, plus Auditor role (P24 Reza Tehrani persona) who has read-only access to the full audit trail for all decisions

- Auditor access: read-only — no state transitions, no field edits, no evidence additions; the Auditor role has zero write permissions across the entire platform

- Audit trail is displayed in the Decision Workspace as a chronological event timeline

- Audit trail is included in the Governance Dashboard report (Reporting Engine) for the configured reporting period

8.3  Immutability Guarantees

- decision_audit_log rows have no UPDATE or DELETE permissions for any application role — enforced at the PostgreSQL role level

- Row-Level Security policy: INSERT only; SELECT filtered by tenant_id; UPDATE and DELETE denied for all application service accounts

- No 'edit audit' or 'delete audit' capability exists in Green PM Studio or any API endpoint — any such capability would require a direct database change by a DBA, which is logged in Cloud SQL audit logs

- Audit log is exportable to CSV or JSON by Studio Admin for external audit purposes — exported file includes a SHA-256 hash of the full export for integrity verification

8.4  Compliance and Legal Hold

For projects subject to regulatory or legal requirements, the Decision audit trail can be placed on legal hold:

- Legal hold flag on a Decision record prevents the record from transitioning to ARCHIVED and prevents any cleanup operations

- Legal hold is set by Studio Admin only; cannot be self-set by any project role

- All audit log entries for legal-hold decisions are retained indefinitely regardless of the standard 7-year retention policy

- Legal hold status is visible in the Decision Workspace with a prominent indicator and included in audit exports