Green PM  v5

Project Command Centre

Executive Intelligence Interface — Technical Reference

Version 5.0  |  August 2026

1.  Philosophy

"The Project Command Centre is not a dashboard. It is the answer to the questions executives ask at 7am on Monday morning: Is the project on track? Where are the risks? What decisions need my attention? What is the project actually ready for?"

The Project Command Centre (PCC) is Green PM's executive interface — an 8-panel intelligence system that continuously translates the full state of the Project Intelligence Graph into answers that EPC executives can act on. Every panel answers a specific question. Every metric has evidence. Every alert is actionable.

The PCC is not a reporting tool. Reports are periodic. The PCC is continuous. Firestore subscriptions push updates to every panel the instant underlying data changes. When a drawing is issued IFC, Panel 6 updates. When a risk is escalated, Panel 4 updates. When a decision is submitted for approval, Panel 8 updates — simultaneously, in real time, for every user with the panel open.

1.1  Executive Digital Twin (EDT)

The Executive Digital Twin is the centrepiece of the PCC. It is architecturally distinct from the Project Intelligence Graph:

- PIG (Project Intelligence Graph): stores reality — all entities, all relationships, all events, continuously updated via event-driven Pub/Sub

- EDT (Executive Digital Twin): summarises reality — a structured weekly snapshot of where the project stands, where it is heading, and what the executive must decide

EDT Generation Schedule:

- Automated weekly run: every Monday 06:00 — Cloud Scheduler triggers Pub/Sub → EDT Generator Cloud Run service

- On-demand refresh: any authorised user can trigger a full regeneration at any time

- Partial refresh: triggered automatically by major events — change order approved, critical milestone impacted, high-severity risk raised

EDT Generation Pipeline:

- Forecasting Engine → schedule trajectory (completion date P50/P80), cost trajectory (final cost P50/P80)

- Recommendation Engine → top 10 prioritised, evidence-backed recommendations for the week

- Decision Engine → open decisions in pending_review or under_review state requiring executive sign-off

- Organizational Memory Engine → institutional context: similar past project state, past decisions, patterns

EDT Three Panels:

- Reality: current project state with evidence — schedule SPI, cost CPI, Evidence Score distribution, active risk count, open decision count; every number is backed by evidence references in the PIG

- Forecast: trajectory — completion date P50/P80, final cost P50/P80, COD Readiness score (Readiness Engine), cash flow forecast

- Required Decisions: 3-5 decisions requiring executive sign-off this week, ranked by schedule/cost impact; each shows: title, decision type, impact summary, recommended option from Organizational Memory Engine, evidence count, urgency

No charts without narrative context. No KPIs without trend direction. The EDT is designed to be read in under 5 minutes and acted on immediately.

2.  The 8 Panels

Every panel in the Project Command Centre answers a specific executive question. Data flows from the Project Intelligence Graph via Firestore real-time subscriptions — every panel updates immediately when the underlying data changes. Panel visibility is role-controlled (see Section 3).

Panel 1 — Executive Summary (Executive Digital Twin)

Primary question: "Is this project on track to deliver on time and within budget?"

Reality section:

- Schedule Performance Index (SPI): current period value with trend arrow (vs last period)

- Cost Performance Index (CPI): current period value with trend arrow

- Evidence Score distribution: breakdown of all project activities by evidence score band — High (>0.7), Medium (0.4-0.7), Low (0.1-0.4), None (0)

- Active risks: count by severity — Critical / High / Medium; delta from last EDT

- Open decisions: count by state — pending_review / under_review / deferred

Forecast section:

- Completion date P50 and P80 (Monte Carlo simulation output from Forecasting Engine)

- Final project cost P50 and P80

- COD Readiness Score — composite score from Readiness Engine across all 6 gates

- Cash flow forecast: next 3 months

Required Decisions (EDT sign-off queue):

- 3-5 decisions requiring executive sign-off this week, ranked by combined schedule and cost impact

- Each card shows: decision title, decision type, impact summary (days / currency), recommended option (Organizational Memory Engine), evidence count cited, deadline for response

Update mechanism: Generated weekly (Monday 06:00) + on-demand refresh + partial refresh on major events.

Role visibility: Executive, Project Director, PMO.

Panel 2 — Schedule Intelligence

Primary question: "What activities are critical? Where is the float?"

Metrics shown:

- CPM summary: total active activities, critical path count, near-critical count (float < 5 days), total float consumed this period

- Critical path activity list: activity ID, name, planned finish, forecast finish, total float, responsible discipline

- Float heatmap: colour-coded grid by work package — red (float < 0 days), amber (0-5), yellow (5-14), green (>14)

- Predecessor analysis: activities whose predecessors are incomplete, with days late

- Activities at risk: float < 5 days, ranked by schedule impact — the 'watch list'

- Milestone forecast: next 5 milestones — planned date, forecast date, variance in days, status pill

- Near-critical activities: float 5-14 days, monitoring list, sorted by proximity to critical

Data sources: Dependency & Chain Analysis Engine (CPM computation over PIG traversal), Forecasting Engine (milestone dates from schedule model).

Update mechanism: Real-time via PIG traversal result cache; recalculated on every schedule event (progress update, predecessor completion, date change).

Role visibility: Project Director, Planner, PMO, Executive.

Panel 3 — Change Intelligence

Primary question: "What changes are affecting the project? What do I need to approve?"

Metrics shown:

- Open changes by impact level: Critical / High / Medium / Low — count and combined cost impact

- Approval queue: changes awaiting this user's approval, sorted by deadline; shows: change title, type, cost impact, schedule impact, evidence count

- Budget variance from changes: approved change value vs original approved budget — total authorised vs original contract sum

- Most impactful pending change: PIG traversal showing full impact chain — affected activities, affected drawings, affected materials, affected milestones, with cascade summary

- Change velocity: changes raised this week vs last week (trend indicator — accelerating / stable / decelerating)

- Change type breakdown: scope, design, commercial, regulatory, weather, other — pie / bar summary

Data sources: Change Intelligence Engine (change records, approval queues), Impact Analysis Engine (PIG traversal per change for cascade impact).

Update mechanism: Real-time — updates on every change event (new change raised, status transition, approval action taken).

Role visibility: Executive (approval queue + summary only), Project Director, Change Manager, PMO.

Panel 4 — Risk & Forecast

Primary question: "What could go wrong? What's the worst case?"

Metrics shown:

- Risk heat map: 5x5 probability-by-impact matrix, colour-coded by zone (red / amber / yellow / green); each cell shows risk count

- Top 5 risks: ranked by risk score (probability x impact x proximity); shows: risk title, score, owner, mitigation status, days to trigger

- Monte Carlo schedule outputs: P50 / P80 / P90 completion dates with confidence interval

- Monte Carlo cost outputs: P50 / P80 / P90 final cost with confidence interval

- Readiness gates summary: 6 gates — Engineering, Material, Construction, Quality, Commissioning, COD — each showing percentage complete and blocking item count

- Risks with no mitigation plan: count and list (action required — Recommendation Engine alert)

- Risk trend: new risks this week, closed risks this week, net change vs last week

Data sources: Risk Engine (risk register, heat map, Monte Carlo inputs), Forecasting Engine (Monte Carlo execution, P-values), Readiness Engine (gate status per gate type).

Update mechanism: Nightly (full Monte Carlo recalculation by Forecasting Engine scheduler) + real-time (new risk event, risk status change, mitigation update).

Role visibility: All roles.

Panel 5 — Vendor & Supply Chain

Primary question: "Are vendors performing? Will materials arrive on time?"

Metrics shown:

- Vendor scorecards: top 5 vendors by composite score and bottom 3 vendors by composite score — shows 6-dimension radar: quality, delivery, responsiveness, documentation, commercial, relationship

- Material readiness score: overall percentage of materials confirmed on-site or confirmed in transit with verified ETA

- Critical dispatches: dispatches on or affecting the critical path — ETA, risk flag (on-time / at-risk / overdue), days to required-on-site date

- Overdue deliveries: count, combined value, maximum schedule impact in days

- Vendor alerts this week: NCRs raised, delivery delays formally notified, documentation submissions outstanding

- Supply chain heat map: by discipline — showing material readiness level per work package

Data sources: Vendor Intelligence Engine (6-dimension scorecards, NCRs, performance causal attribution), Supply Chain Intelligence Engine (material readiness scoring, 10-stage dispatch lifecycle).

Update mechanism: Real-time on dispatch events (dispatch created, status updated, ETA changed, received) + daily batch scorecard recalculation.

Role visibility: Project Director, Procurement Manager, PMO, Executive.

Panel 6 — Engineering & Readiness

Primary question: "Is engineering progressing? Are we ready for construction?"

Metrics shown:

- Drawing register status: IFC percentage, pending-review percentage, revision-in-progress count — broken down by discipline

- Drawings on critical path: count of critical-path activities with pending IFC drawings; those overdue for issue

- Engineering Readiness gate: overall gate status (% complete), blocking item count, and named blocking items

- Construction Readiness gate: overall gate status (% complete), blocking item count, responsible party per item

- Drawing revision conflicts: drawings with active consistency alerts from Synchronization & Consistency Engine (e.g., drawing Rev D specifies equipment not in PO; drawing conflicts with specification)

- RFI backlog: open RFIs by age bucket — less than 7 days / 7-14 days / over 14 days; total count and oldest open RFI date

Data sources: Drawing workspace data via PIG (revision history, IFC status, RFI log), Readiness Engine (gate criteria completion per gate), Synchronization & Consistency Engine (drawing conflict detection).

Update mechanism: Real-time on drawing events — upload, IFC issue, revision created, RFI raised, comment resolved.

Role visibility: Engineering Manager, Project Director, PMO, Executive.

Panel 7 — Evidence & Quality

Primary question: "How much evidence do we have? What's unverified?"

Metrics shown:

- Evidence score distribution: histogram of all active activity evidence scores — High (>0.7), Medium (0.4-0.7), Low (0.1-0.4), None (0); total count per band

- Activities with verification_required flag: count and list by discipline — these are activities with evidence flagged for manual verification

- Activities with zero evidence: count, percentage of total active activities, and list of critical-path activities with zero evidence (highest risk)

- QA/QC inspection pass rate: inspections passed vs total inspections conducted this reporting period

- Evidence ingestion rate: evidence items captured this week vs last week (trend: increasing / stable / decreasing)

- Capture type breakdown: photos / videos / voice memos / IoT sensor readings / inspection records / test certificates / document uploads — count and percentage mix

Data sources: Evidence Engine (Evidence Score v5 computation, ingestion pipeline, verification flags), QA/QC inspection records in PIG.

Update mechanism: Real-time on evidence ingestion events — every photo upload, voice memo, sensor reading, and document import triggers an immediate update.

Role visibility: QA/QC Manager, Site Manager, Project Director, PMO, Auditor.

Panel 8 — Decisions & Actions

Primary question: "What decisions are open? What actions are overdue?"

Metrics shown:

- Open decisions by state: pending_review / under_review / deferred — count per state and oldest item age per state

- Decisions overdue for response: decisions in pending_review or under_review with no action by the assigned approver for > 48 hours — with escalation status

- Coordination items by status: pending / acknowledged / in_progress / overdue / closed — count per status; overdue items highlighted

- Overdue coordination items: count and named list, grouped by responsible party, with days overdue

- Open action items: by assignee, due date, and priority — all users can see their own; Project Director sees all

- Decision throughput: decisions closed this week vs decisions raised this week (resolution velocity — is governance keeping up with events?)

Data sources: Decision Engine (decision records and state machine), Coordination Engine (coordination item lifecycle — event to closure).

Update mechanism: Real-time via Firestore subscription — updates immediately on any decision state transition or coordination item status change.

Role visibility: All roles — filtered to user's own items by default; Project Director and PMO see all items.

3.  Role-Based Panel Configuration

Each role has a default panel configuration defined in Green PM Studio (Role & Permission Builder). Defaults can be overridden per tenant. Hidden panels cannot be accessed by that role unless explicitly unlocked.

| Role | Default Panels | Hidden Panels | Custom Widgets Available |
| --- | --- | --- | --- |
| Executive | 1 (EDT), 4 (Risk & Forecast), 8 (Decisions & Actions) | 7 (Evidence detail), 6 (Engineering detail), 5 (Vendor detail), 2 (Schedule detail) | COD Readiness Gauge, Decision Sign-off Queue, SPI/CPI Trend |
| Project Director | All 8 panels | None | All widgets available |
| PMO | 1, 2, 3, 4, 8 | 5 (Vendor detail) | Milestone Tracker, Change Budget Summary, Risk Heatmap |
| Engineering Manager | 2 (Schedule), 6 (Engineering), 7 (Evidence) | 5, 8 | Drawing Status Board, RFI Tracker, IFC Progress Chart |
| Procurement Manager | 5 (Vendor & Supply Chain) | 1, 2, 3, 4, 6, 7, 8 | Vendor Scorecard, Dispatch Tracker, Material Readiness Gauge |
| QA/QC Manager | 7 (Evidence & Quality), 6 (Engineering) | 1, 3, 5 | Inspection Pass Rate, Evidence Score Trend, Zero-Evidence List |
| Site Manager | 2 (Schedule), 6 (Engineering), 7 (Evidence), 8 (Decisions) | 1, 3, 5 | Activity Evidence Board, Coordination Items, Daily Float Summary |
| Commissioning Manager | 4 (Risk), 6 (Engineering), 8 (Decisions) | 3, 5, 7 | Readiness Gate Status, COD Tracker, System Completion List |
| Auditor | 7 (Evidence), 8 (Decisions — read-only) | 1, 2, 3, 4, 5, 6 | Evidence Audit Trail (read-only), Decision Log (read-only) |
| Vendor Portal User | 5 (own scorecard + dispatches only) | 1, 2, 3, 4, 6, 7, 8 | Own Delivery Performance, Own NCR Log |

Note: Panel visibility is enforced server-side — hidden panels return 403 Forbidden on direct API calls. Client-side hiding is a UX convenience only, not a security control.

4.  Mobile Command Centre

The Mobile Command Centre is the project-site-optimised view of the PCC — same intelligence, same real-time data, adapted for a 375px-wide viewport. It is not a separate application: the web application responds to device viewport and renders a stacked, touch-optimised layout.

4.1  Design Principles

- Same 8 panels, stacked vertically in role-priority order

- Each panel shows its single most important metric — the 'key metric' — with a trend indicator (up/down/stable arrow)

- Tap any panel card to expand to full panel detail view

- Panel order is role-defaulted and further configurable in Green PM Studio (Role & Permission Builder)

- Push notifications via FCM — critical alerts deep-link directly to the relevant panel

- Offline mode: last-loaded panel state is available offline; sync resumes when connectivity returns

4.2  Key Metric by Panel (Mobile Default)

| Panel | Key Metric (Mobile) | Alert Threshold for Push Notification |
| --- | --- | --- |
| 1 — EDT | SPI + CPI combined status pill: On Track / At Risk / Critical | CPI < 0.9 or SPI < 0.9 |
| 2 — Schedule | Critical path count + float trend direction | New activity joins critical path |
| 3 — Change | Pending approvals count + total pending budget impact | Approval overdue > 24h |
| 4 — Risk & Forecast | Active Critical risks count + schedule P80 date | New Critical risk raised |
| 5 — Vendor & Supply Chain | Material readiness score % + overdue deliveries count | Critical material overdue |
| 6 — Engineering | IFC percentage + drawing conflicts count | Drawing on critical path overdue IFC |
| 7 — Evidence | Evidence coverage % (activities with score > 0.4) + unverified count | Critical path activity with zero evidence |
| 8 — Decisions & Actions | Open decisions count + overdue items count | Decision overdue > 48h |

4.3  Implementation Notes

- Responsive breakpoints: desktop >= 1024px (full 8-panel grid), tablet 768-1023px (2-column stacked), mobile < 768px (single-column stacked)

- Same Firestore subscriptions as desktop — no separate mobile API; data is identical

- Evidence capture (photos, voice) accessible from mobile via Panel 7 expand view — taps into native camera and microphone APIs via the mobile browser

- FCM push notifications require user opt-in per device — managed in Green PM Studio (Notification Rule Builder)